## M1
Req ID | Requirement | Priority | Source (Stakeholder) | Stakeholder Need | Acceptance Criteria ID | Acceptance Criteria | Status | Design Link | Test Evidence | Change History | Release Evidence
FR-01 | The system shall allow citizens to submit an incident report with a photo and GPS coordinates. | Must | Citizens/Residents | Fast issue reporting, easy to use interface | AC-FR-01 | Given that a citizen opens the report form when they attach a photo and submit, then the report includes GPS coordinates | Proposed | TBD | TBD | TBD | TBD
FR-02 | The mobile interface shall support offline caching of assigned job cards and sync updates once network connectivity is restored. | Must | Municipal Field Workers/Technicians | Clear work orders offline capability, status update tools | AC-FR-02 | Given a field worker device is offline, when job cards are assigned, then they must be cached locally and remain fully accessible and editable without connectivity. | Proposed | TBD | TBD | TBD | TBD
FR-03 | The platform should generate a map of unresolved municipal faults categorized per department. | Should | Municipal Administrators/Management | Analytics dashboards, resource allocation tools | AC-FR-03 | When the reporting cycle changes, then a map should generate with department and fault status. | Proposed | TBD | TBD | TBD | TBD
FR-04 | The system shall provide a role-based administration dashboard for routing, updating, and closing support tickets. | Must | Municipal Administrators/Management | Resource allocation tools, audit trails | AC-FR-04 | Given an administrator logs in, when they access the dashboard, then they must be able to view, assign, update, and close tickets based on their role permissions. | Proposed | TBD | TBD | TBD | TBD
FR-05 | The system shall send notifications when the report status changes. | Should | Citizens/Residents | Transparent progress updates | AC-FR-05 | Given a citizen has submitted a report when the report status changes to Assigned, In Progress, or Resolved, then an alert is sent on the website. | Proposed | TBD | TBD | TBD | TBD
FR-06 | The system shall allow citizens to track the status of their reported issues via a unique tracking number. | Could | Citizens/Residents | Transparent progress updates | AC-FR-06 | Given a citizen has a tracking number, when they enter it into the tracking portal, they must then see the status and complete history of their report. | Proposed | TBD | TBD | TBD | TBD
FR-07 | The system shall allow field workers to update job status with photos and notes from the field. | Could | Municipal Field Workers/Technicians | Status update tools | AC-FR-07 | Given a field worker is on-site at a job location, when they update a job status, then they must be able to attach at least one photo and enter textual notes as part of the update. | Proposed | TBD | TBD | TBD | TBD
NFR-01 | The mobile interface must complete a full offline to online data sync less than 10 seconds of network reconnection, for job cards containing up to twenty pending status updates. | Must | Municipal Field Workers/Technicians | Offline capability | AC-NFR-01 | Given a field worker device has been offline with up to twenty cached job card updates, when connectivity is restored, then all updates must be confirmed as synced to the server less than 10 seconds, with a visible confirmation indicator on the device. | Proposed | TBD | TBD | TBD | TBD
NFR-02 | The web interface shall have an average response time of under three seconds during peak usage hours between 9 AM and 5 PM. | Must | Citizens/Residents | Fast issue reporting | AC-NFR-02 | Given one hundred concurrent users are accessing the system during peak hours when any page is requested, then the median response time across all requests must be under three seconds. | Proposed | TBD | TBD | TBD | TBD
NFR-03 | The system shall ensure all citizen submitted data is transmitted over HTTPS with TLS | Must | Municipal Administrators/Management | Security, compliance | AC-NFR-03 | Given a citizen submits a report when the data is transmitted, then it must be encrypted using HTTPS with TLS as verified by browser security inspection tools. | Proposed | TBD | TBD | TBD | TBD
NFR-04 | The mobile web interface shall be responsive and fully functional on screens as small as 360 pixels width. | Could | Citizens/Residents | Easy-to-use interface | AC-NFR-04 | Given a user accesses the system on a device with a 360 pixels screen width, when they navigate the interface, then all features must be accessible and usable without horizontal scrolling. | Proposed | TBD | TBD | TBD | TBD
NFR-05 | The system shall achieve 99.5%uptime during operational hours | Should | Municipal Administrators/Management | Reliability | AC-NFR-05 | Given the system is in production, when availability is measured over a thirty-day period, then uptime must be at least 99.5%during operational hours. | Proposed | TBD | TBD | TBD | TBD

## M2
Req ID | Requirement | Stakeholder & Priority | Acceptance Criteria | ASR | Architecture | Data Persistence | Design Decision | Techonology Decision | Implementation Evidence | Verification Evidence | Status | ADR & Changes
FR-01 | The system shall allow citizens to submit an incident report with a photo and GPS coordinates. | Citizens/Residents; Must | ACFR-01: Given a citizen opens the report form, when they attach a photo and submit, then the report includes GPS coordinates. | ASR-05 (low bandwidth/PWA); ASR-07 (testability); POPIA/security constraint | Presentation: Citizen Web UI; Application: API Controllers, Validation; Domain: Request Factory; Persistence: ServiceRequest repository | ServiceRequest: CitizenID, CategoryID, Description, PhotoReference, Latitude, Longitude, Status, Version, CreatedAt, UpdatedAt; POPIA location/photo data | ED-009 Factory Method for category creation; Browser Geolocation and Media Capture APIs; layered validation (client usability, application rules, DB constraints) | React 18 + Vite 5 + TypeScript 5; Express 4; Zod 3; Prisma 5; PostgreSQL 16 | TBD | Planned: timed submission test; GPS captured; photo attached; automated factory-extension test | Planned — Not Yet Implemented | ED-009; ADR-TECH-01; ADR-PERSIST-01; RR-006; RR-004; v1.0 baselined; v2.0 design link added
FR-02 | The mobile interface shall support offline caching of assigned job cards and sync updates once network connectivity is restored. | Municipal Field Workers/Technicians; Must | ACFR-02: Given a field worker device is offline, when job cards are assigned, then they must be cached locally and remain fully accessible and editable without connectivity. | ASR-01 (offline-first sync); ASR-05 (intermittent connectivity) | Presentation: Field Worker PWA; Domain: Sync/Conflict Resolver; Persistence: repositories; Service Worker/IndexedDB | Client IndexedDB cache; server ServiceRequest/Assignment status; Version column for optimistic concurrency | FE-001 technical spike; conflict strategy ADR TBD; ADR-PERSIST-01 version-column concurrency | Workbox 7; IndexedDB via idb; React PWA; Express sync endpoint; Prisma/PostgreSQL | TBD | Planned: airplane-mode test; 20 offline updates; reconnect and confirm sync <10 s | Planned — Not Yet Implemented | ADR-TECH-01; ADR-PERSIST-01; RR-001; RR-132; FE-001
FR-03 | The platform should generate a map of unresolved municipal faults categorized per department. | Municipal Administrators/Management; Should | ACFR-03: When the reporting cycle changes, then a map should generate with department and fault status. | ASR-04 (reporting/analytics); ASR-07 (measurable acceptance) | Domain: Reporting Service; Presentation: Admin Dashboard; Persistence: reporting queries | ServiceRequest, Category, Assignment, Department; indexes on department/status; aggregate view | ED-009 department routing per category; ADR-PERSIST-01: no status caching; aggregate cache only with TTL and invalidation on write | React dashboard; Express API; Prisma/PostgreSQL; indexing/aggregation strategy | TBD | Planned: load one week fault data; advance clock; verify map by department and status | Planned — Not Yet Implemented | ED-009; ADR-PERSIST-01; FE-006; RR-075; RR-076
FR-04 | The system shall provide a role-based administration dashboard for routing, updating, and closing support tickets. | Municipal Administrators/Management; Must | ACFR-04: Given an administrator logs in, when they access the dashboard, then they must be able to view, assign, update, and close tickets based on their role permissions. | ASR-03 (RBAC/audit); ASR-04 (reporting/activity) | Presentation: Admin Dashboard; Application: Auth Middleware; Domain: RBAC Policy Engine, Workflow Service | ServiceRequest, Assignment, StatusHistory; role checks; audit trail | ADR-PERSIST-01: update/close is a status transition; workflow state machine and role permissions enforced in application layer, DB constraints as backstop; RBAC central module; ED-009 routing per category | React 18; Express 4; JWT + bcrypt; Prisma 5; PostgreSQL 16 | TBD | Planned: log in with each role; verify each role reaches only permitted actions and data; server-side permission tests | Planned — Not Yet Implemented | ADR-ARCH-01; ADR-PERSIST-01; ADR-TECH-01; RR-083; RR-130; RR-122; v1.0 baselined; v2.0 design link added
FR-05 | The system shall send notifications when the report status changes. | Citizens/Residents; Should | ACFR-05: Given a citizen has submitted a report, when the report status changes to Assigned, In Progress, or Resolved, then an alert is sent on the website. | ASR-02 (real-time transparency); ASR-03 (audit/accountability); ASR-08 (audit retention) | Domain: Workflow Service (subject), Notification Service (observer), Domain Events; Application: API | ServiceRequest status; StatusHistory append-only; Assignment; post-commit event only | ED-008 Observer; ADR-INT-01 in-process event-based integration; ADR-PERSIST-01 transactional status transition; post-commit dispatch | Node/Express in-process domain events; Prisma 5 / PostgreSQL 16; React in-app notification | TBD | Planned: status-change alert test; new-observer test (no subject modification); rollback no-event test | Planned — Not Yet Implemented | ADR-INT-01; ADR-PERSIST-01; ED-007; ED-008; RR-081; RR-093
FR-06 | The system shall allow citizens to track the status of their reported issues via a unique tracking number. | Citizens/Residents; Could | ACFR-06: Given a citizen has a tracking number, when they enter it into the tracking portal, they must then see the status and complete history of their report. | ASR-02 (transparency); ASR-08 (history/audit) | Domain: Workflow/Reporting; Persistence: StatusHistory; Presentation: tracking portal | ServiceRequest tracking number unique; StatusHistory history rows | ADR-PERSIST-01 append-only history; non-sequential random identifier (RR-110); server-side ownership/lookup checks (RR-114) | PostgreSQL 16 unique constraint; Prisma 5; React portal | TBD | Planned: submit, obtain number, enter in portal, verify status/timestamps; uniqueness and unpredictability test | Planned — Not Yet Implemented | ADR-PERSIST-01; RR-110; RR-114; RR-064
FR-07 | The system shall allow field workers to update job status with photos and notes from the field. | Municipal Field Workers/Technicians; Could | ACFR-07: Given a field worker is onsite at a job location, when they update a job status, then they must be able to attach at least one photo and enter textual notes as part of the update. | ASR-01 (offline/field); ASR-02 (status transparency); ASR-08 (audit) | Presentation: Field Worker PWA; Domain: Workflow Service; Persistence: repositories | StatusHistory with actor, timestamp, old/new status; ServiceRequest; photo/notes | ADR-PERSIST-01 transactional status update; Browser Media Capture API; sanitise/encode notes before rendering (RR-113) | React PWA; Workbox 7 / IndexedDB; Express; Prisma 5 / PostgreSQL 16 | TBD | Planned: on-site update with photo and notes; XSS test on notes fields | Planned — Not Yet Implemented | ADR-PERSIST-01; RR-113; RR-129
FR-08 | The system shall allow citizens to view a history of their submitted service requests (status, date, category). | Citizens/Residents; Could | ACFR-08: Given an authenticated citizen opens their request history, when the history is displayed, then each of their submitted requests must show its current status, submission date and category, and the citizen must only be able to see their own requests. | ASR-02 (transparency/history) | Presentation: Citizen Web UI; Domain: Reporting Service; Persistence: query layer | ServiceRequest history; pagination/lazy loading; server-side ownership checks | Design constraints known: RR-074 (pagination or lazy loading), RR-114 (server-side ownership checks on every lookup), RR-124 (duplicate-account detection). Detailed design not yet produced. | React; Express; Prisma 5 / PostgreSQL 16 | TBD | Planned: multiple reports with mixed statuses on seeded accounts (RR-058); identifier-manipulation test (RR-114) | Planned — Not Yet Implemented | RR-058; RR-074; RR-114; RR-124; v2.0 added
FR-09 | Staff shall be able to search, filter and sort service requests. | Municipal Field Workers/Technicians; Must | ACFR-09: Given authenticated staff search, filter or sort service requests, when results are returned, then the results must be scoped to that staff member's role permissions and must accurately match the applied filter/sort criteria without silently omitting matching records | ASR-04 (reporting/filtering) | Presentation: Admin Dashboard; Domain: Reporting Service; Persistence: indexed queries | Indexes on filter/sort fields; server-side role-scoped filtering | Design constraints known: indexes around filter/sort fields (RR-075), server-side role-scoped filtering (RR-108), conventional filter UI (RR-121). Detailed schema design in M2 not yet produced. | React; Express; Prisma 5 / PostgreSQL 16 | TBD | Planned: edge-case matrix (empty results, combined/invalid filters) (RR-059); results validated against manually verified data set (RR-126) | Planned — Not Yet Implemented | RR-059; RR-075; RR-108; RR-121; RR-126; v2.0 added
FR-10 | Staff shall be able to be assigned to, and accept, service requests (job assignment/acceptance). | Municipal Field Workers/Administrators; Must | ACFR-10: Given a service request is available for assignment, when two staff members attempt to accept the same request simultaneously, then only one acceptance may succeed and the other must be rejected with a visible conflict indication, and the acceptance must be recorded in the audit log with a consistent acting-user identifier. | ASR-03 (RBAC/audit); ASR-04 (activity analytics) | Domain: Workflow Service; Application: RBAC; Presentation: Admin/Field UI | Assignment; ServiceRequest version; StatusHistory; optimistic concurrency | ADR-PERSIST-01: assignment change inside status-transition transaction; version column so only one acceptance succeeds (A2 lost-update case) | Prisma 5 / PostgreSQL 16 transactions; Express; React | TBD | Planned: simultaneous accept concurrency test (only one succeeds) (RR-060); assignment/acceptance events appear in audit log (RR-125) | Planned — Not Yet Implemented | ADR-PERSIST-01; RR-060; RR-083; RR-122; RR-125; v2.0 added
FR-11 | The system shall provide a management performance dashboard (aggregated request metrics and staff activity summaries). | Municipal Administrators/Management; Should | ACFR-11: Given request and staff activity data exists, when a manager opens the performance dashboard, then the aggregated metrics must match values calculated manually from the same underlying data set, and timestamps shown must be consistent with the request history view. | ASR-03 (audit/accountability); ASR-04 (reporting/analytics); ASR-08 (retention) | Presentation: Admin Dashboard; Domain: Reporting Service; Persistence: aggregation | Aggregate summaries; pre-aggregated tables; anonymise citizen detail; UTC storage | Separate aggregation from presentation (RR-088); pre-aggregated summaries rather than live queries (RR-076); single status enumeration (RR-122); anonymise citizen detail (RR-115); UTC storage (RR-127); FE-006 | React + charting library; Express; Prisma 5 / PostgreSQL 16 | TBD | Planned: dashboard figures cross-checked against manually calculated seed data (RR-061); timestamp consistency across dashboard and history (RR-127) | Planned — Not Yet Implemented | RR-061; RR-076; RR-088; RR-115; RR-122; RR-127; FE-006; v2.0 added
FR-12 | The system must make staff and admins authenticate accounts before log in. | Municipality Field Workers/Administrators; Must | ACFR-12: Given a user registers or logs in, when valid credentials are supplied, then access is granted; when invalid, duplicate or boundary inputs are supplied, then the attempt is rejected with a user-friendly message and failed logins are logged without sensitive data; new registrations default to the lowest-privilege role. | ASR-03 (security/RBAC); ASR-07 (testability) | Application: Auth Middleware; Domain: RBAC; Presentation: registration/login | Citizen/Officer accounts; JWT/bcrypt; failed-login logs; session data | Established auth/hashing libraries (RR-112, RR-144); rate limiting (RR-104); lowest-privilege default role (RR-130); duplicate detection (RR-124); secure password reset if added (RR-133); concurrent-session behaviour (RR-134); failed-login logging (RR-135); POPIA re-review (RR-139) | JWT + bcrypt; Express; Prisma 5 / PostgreSQL 16; Zod 3 | TBD | Planned: authentication suite (valid, invalid, duplicate, boundary, failed-login) (RR-062); staging validation (RR-098) | Planned — Not Yet Implemented | ADR-TECH-01; RR-062; RR-098; RR-104; RR-111; RR-112; RR-124; RR-130; RR-133; RR-134; RR-135; RR-139; RR-144; v2.0 added
FR-13 | The system shall allow field workers to search job cards by location/proximity (search point and radius). | Municipal Field Workers/Technicians; Could | ACFR-13: Given a field worker provides a search point and radius, when the proximity search is executed, then job cards within the radius must be returned and job cards outside the radius excluded, and precise location data must only be visible to authorised roles. | ASR-04 (filtering/analytics); ASR-05 (field connectivity) | Presentation: Field Worker PWA; Domain: Reporting/Geospatial Service; Persistence: spatial query | Geospatial indexing; precise location masking/generalisation | Design constraints known: lightweight geospatial indexing on free tier (RR-077); mask or generalise precise location outside authorised roles (RR-109); geospatial query research (RR-145); environment configuration (RR-093). Stack evaluation in M2 not yet complete. | PostgreSQL 16 geospatial indexing to be evaluated; Prisma 5; Express; React | TBD | Planned: seeded job-card locations at varying distances/radii (RR-063); real-device field test (RR-102) | Planned — Not Yet Implemented | RR-063; RR-077; RR-093; RR-102; RR-109; RR-145; v2.0 added
FR-14 | The system shall issue a unique acknowledgment receipt (including tracking number and submission summary) when a report is submitted. | Citizens/Residents; Could | ACFR-14: Given a citizen submits a valid report, when the submission succeeds, then a receipt must be issued containing a unique, non-sequential tracking number and a summary that matches the submitted data exactly. | ASR-02 (transparency); ASR-07 (measurable acceptance) | Domain: Workflow Service; Presentation: Citizen Web UI; Persistence: identifiers | Unique tracking number; receipt generated from validated submission data | Design constraints known: non-sequential random identifiers (RR-110); receipt generated from same validated submission data (RR-128). Detailed design not yet produced. | Prisma 5 / PostgreSQL 16 unique constraint; React | TBD | Planned: large batch of test submissions confirming uniqueness (RR-064); receipt matches submission (RR-128) | Planned — Not Yet Implemented | RR-064; RR-110; RR-128; v2.0 added
FR-15 | The system shall display an estimated resolution time to citizens for their requests. | Citizens/Residents; Could | ACFR-15: Given historical resolution data exists for a category, when a citizen views a request, then an estimated resolution time must be displayed in plain language and labelled provisional where the estimate is based on limited historical data. | ASR-04 (reporting/analytics); ASR-07 (testability) | Domain: Reporting Service; Presentation: Citizen UI | Category-level estimates cached or recomputed periodically; historical data | Design constraints known: category-level estimates cached or recomputed periodically (RR-079); early estimates labelled provisional (RR-123); plain-language wording (RR-119). Detailed design not yet produced. | Prisma 5 / PostgreSQL 16; caching/recompute strategy | TBD | Planned: estimation against seeded historical data of varying category/workload (RR-065); wording user-tested with non-technical reviewers (RR-119) | Planned — Not Yet Implemented | RR-065; RR-079; RR-119; RR-123; v2.0 added
NFR-01 | The mobile interface must complete a full offline to online data sync within less than 10 seconds of network reconnection, for job cards containing up to twenty pending status updates. | Municipal Field Workers/Technicians; Must | ACNFR-01: Given a field worker device has been offline with up to twenty cached job card updates, when connectivity is restored, then all updates must be confirmed as synced to the server within less than 10 seconds, with a visible confirmation indicator on the device. | ASR-01 (offline sync); ASR-05 (low bandwidth) | Presentation: Field Worker PWA; Domain: Sync/Conflict Resolver; Persistence: sync endpoint | Client IndexedDB; server ServiceRequest/Assignment; version concurrency | FE-001 spike (service worker sync patterns); conflict strategy ADR TBD; ADR-PERSIST-01 version concurrency; PED Quality Constraint 2: efficient sync protocol; frontend conflict resolution | Workbox 7; IndexedDB; Express sync endpoint; Prisma 5 / PostgreSQL 16 | TBD | Planned: 20 offline updates, reconnect, time sync to confirmation indicator <10 s under realistic network conditions | Planned — Not Yet Implemented | ADR-TECH-01; ADR-PERSIST-01; RR-001 (Critical); FE-001
NFR-02 | The web interface shall have an average response time of under three seconds during peak usage hours between 9 AM and 5 PM. | Citizens/Residents; Must | ACNFR-02: Given one hundred concurrent users are accessing the system during peak hours, when any page is requested, then the median response time across all requests must be under three seconds. | ASR-04 (performance/scalability); ASR-06 (availability) | Presentation; Application/API; Reporting; Persistence | Indexing/query optimisation; no status caching; aggregate cache only with measured evidence | ADR-PERSIST-01 caching position: no status caching in v1; cache only read-heavy aggregates, on measured evidence; Indexing and query optimisation (Quality Constraint 3; FE-006) | React/Vite; Express; Prisma 5 / PostgreSQL 16; free-tier PaaS | TBD | Planned: load test 100 concurrent users at peak; median response time <3 s | Planned — Not Yet Implemented | ADR-PERSIST-01; ADR-TECH-01; RR-005; RR-074–076
NFR-03 | The system shall ensure all citizen-submitted data is transmitted over HTTPS with TLS. | Municipal Administrators/Management; Must | ACNFR-03: Given a citizen submits a report, when the data is transmitted, then it must be encrypted using HTTPS with TLS as verified by browser security inspection tools. | ASR-03 (security); ASR-06 (deployment/availability) | Presentation boundary; Application/API; Deployment | Encryption in transit; POPIA compliance | PED Security Constraint 1 (HTTPS/TLS, encryption at rest, POPIA); stack-independent; implementation follows M2 stack/hosting decision (ED-005); pre-deployment HTTPS/TLS checklist (RR-033, referenced by RR-090) | PaaS HTTPS/TLS; Express; React | TBD | Planned: inspect all API calls and form submissions in browser developer tools | Planned — Not Yet Implemented | ADR-TECH-01; RR-004; RR-090
NFR-04 | The mobile web interface shall be responsive and fully functional on screens as small as 360 pixels width. | Citizens/Residents; Could | ACNFR-04: Given a user accesses the system on a device with a 360 pixels screen width, when they navigate the interface, then all features must be accessible and usable without horizontal scrolling. | ASR-05 (low bandwidth/device range); ASR-07 (testability) | Presentation: Citizen/Field UI | None directly | ED-002 (single web-responsive codebase); Technology Constraint 2 (CSS media queries) | React; CSS; Vite | TBD | Planned: 360 px viewport simulation in developer tools | Planned — Not Yet Implemented | ED-002; RR-120
NFR-05 | The system shall achieve 99.5% uptime during operational hours. | Municipal Administrators/Management; Should | ACNFR-05: Given the system is in production, when availability is measured over a thirty-day period, then uptime must be at least 99.5% during operational hours. | ASR-06 (availability) | Deployment: stateless app; health checks; managed DB | Managed PostgreSQL; backup/recovery | FE-003 (hosting path, free-tier limits), FE-004 (monitoring), FE-005 (backup and recovery): M2 stack-decision criteria | Render / Railway / Fly; managed PostgreSQL 16; UptimeRobot / Logtail | TBD | Planned: 30-day availability post-production | Planned — Not Yet Implemented | ADR-ARCH-01; ADR-TECH-01; FE-003; FE-004; FE-005; RR-094
NFR-06 | Audit-log entries shall be retained for ninety days. | Municipal Administrators/Management; Must | ACNFR-06: Given audit-log entries are written, when retention is measured over the configured policy period, then entries must be retained for at least ninety days, with corrections recorded as new entries rather than modifying or deleting existing entries. | ASR-03 (audit/accountability); ASR-08 (audit retention) | Domain: Audit Service; Persistence: append-only store | Append-only StatusHistory/audit table; retention/archival | ADR-PERSIST-01 append-only history; corrections recorded as new entries; single audit-log schema and reusable audit service (RR-137, RR-087); restricted access to log store (RR-107); explicit retention/archival (RR-136, RR-078); POPIA re-review (RR-139) | PostgreSQL 16; Prisma 5; scheduled retention job | TBD | Planned: retention policy test (RR-136); retention config verified in staging (RR-091); audit test cases include FR-10 events (RR-125) | Planned — Not Yet Implemented | ADR-PERSIST-01; RR-078; RR-091; RR-107; RR-125; RR-136; RR-137; v2.0 added
NFR-07 | The system shall meet WCAG 2.1 Level AA accessibility. | Citizens/Residents; Must | ACNFR-07: Given the system is audited with an established accessibility tool, when the audit is run, then all identified issues must meet WCAG 2.1 Level AA success criteria, with keyboard-only navigation and at least two screen reader/browser combinations verified across desktop and mobile views. | ASR-07 (testability/measurable acceptance) | Presentation: UI components | None directly | Design constraints known: accessible components and palette from first mockups (RR-086, RR-117); UI libraries with built-in accessibility (RR-116); accessibility linter in build (RR-072); mobile views included (RR-120). Detailed design not yet produced. | React UI library; axe-core | TBD | Planned: audit-tool compliance checklist (RR-138); more than one screen reader/browser combination (RR-100); keyboard-only paths per screen (RR-118) | Planned — Not Yet Implemented | RR-072; RR-086; RR-100; RR-116; RR-117; RR-118; RR-120; RR-138; v2.0 added
NFR-08 | User sessions shall time out after thirty minutes of inactivity. | All Users; TBD | ACNFR-08: Given an authenticated user is inactive for thirty minutes, when the timeout elapses, then the session must expire server-side and require re-authentication, and unsaved form data should be preserved locally where technically feasible. | ASR-03 (security/session) | Application: Auth Middleware; Domain: RBAC | Session/token store; server-side invalidation | Design constraints known: timeout implemented centrally in authentication layer (RR-131); server-side token invalidation (RR-105); preserve unsaved data on forced re-authentication (RR-132). Detailed authentication design in M2 not yet produced. | JWT; bcrypt; Express; server-side token invalidation | TBD | Planned: timeout test per role (citizen, field worker, admin) (RR-066); staging validation (RR-098) | Planned — Not Yet Implemented | RR-066; RR-098; RR-105; RR-131; RR-132; v2.0 added
NFR-09 | Error handling shall show user-friendly messages without exposing sensitive technical information. | All Users; Must | ACNFR-09: Given an error occurs, when the error response is returned, then the message shown must be user-friendly and must not expose stack traces, query text or other sensitive technical details in any non-development environment. | ASR-07 (testability/error handling) | Application: Error Boundary; central error handler | None directly | Design constraints known: single centralised error-handling layer (RR-084); debug output disabled outside local development (RR-103). Detailed design not yet produced. | Express error middleware; React error boundaries; logging | TBD | Planned: test error responses on all endpoints for leaked internals (RR-106); verify non-development environments (RR-103) | Planned — Not Yet Implemented | RR-084; RR-103; RR-106; v2.0 added
NFR-10 | The system shall function across the four named browsers (Chrome, Firefox, Safari, Edge). | All Users; Should | ACNFR-10: Given the system is tested on Chrome, Firefox, Safari and Edge, when each browser is used, then the system must function and a pass/fail compatibility log must be maintained per milestone. | ASR-05 (browser compatibility); ASR-07 (measurable acceptance) | Presentation | None directly | Design constraint known: PED Technology Constraint 2 (modern browsers; responsive CSS). Detailed design not yet produced. | React; Vite; CSS | TBD | Planned: pass/fail compatibility log per browser for each milestone (RR-140) | Planned — Not Yet Implemented | RR-140; v2.0 added
NFR-11 | Timestamps shall be handled consistently across timezones. | All Users; Could | ACNFR-11: Given timestamps are stored and displayed, when the system is tested with multiple simulated timezones, then timestamps must be stored in a standard reference time, converted correctly for display, and remain consistent across dashboard and history views. | ASR-04 (reporting accuracy); ASR-08 (audit retention) | Application/Domain: shared date utility; Persistence | Store UTC/timestamptz; convert for display; ServiceRequest/StatusHistory timestamps | Design constraints known: shared date/time utility (RR-085); centralised timezone configuration (RR-069, RR-092). Detailed design not yet produced. | PostgreSQL 16 timestamptz; shared JS date utility | TBD | Planned: test with multiple simulated timezones (RR-099); verify server timezone at deployment (RR-092) | Planned — Not Yet Implemented | RR-069; RR-085; RR-092; RR-099; RR-127; v2.0 added

## M3
Req ID | Requirement | Stakeholder & Priority | Acceptance Criteria | ASR | Architecture | Data Persistence | Design Decision | Techonology Decision | Implementation Evidence | Verification Evidence | Status | ADR & Changes
FR-01 | The system shall allow citizens to submit an incident report with a photo and GPS coordinates. | Citizens/Residents; Must | ACFR-01: Given a citizen opens the report form, when they attach a photo and submit, then the report includes GPS coordinates. | ASR-05 (low bandwidth/PWA); ASR-07 (testability); POPIA/security constraint | Presentation: Citizen Web UI; Application: API Controllers, Validation; Domain: Request Factory; Persistence: ServiceRequest repository | ServiceRequest: CitizenID, CategoryID, Description, PhotoReference, Latitude, Longitude, Status, Version, CreatedAt, UpdatedAt; POPIA location/photo data | ED-009 Factory Method for category creation; Browser Geolocation and Media Capture APIs; layered validation (client usability, application rules, DB constraints) | React 18 + Vite 5 + TypeScript 5; Express 4; Zod 3; Prisma 5; PostgreSQL 16 | TBD | TBD | In Development | ED-009; ADR-TECH-01; ADR-PERSIST-01; RR-006; RR-004; v1.0 baselined; v2.0 design link added
FR-02 | The mobile interface shall support offline caching of assigned job cards and sync updates once network connectivity is restored. | Municipal Field Workers/Technicians; Must | ACFR-02: Given a field worker device is offline, when job cards are assigned, then they must be cached locally and remain fully accessible and editable without connectivity. | ASR-01 (offline-first sync); ASR-05 (intermittent connectivity) | Presentation: Field Worker PWA; Domain: Sync/Conflict Resolver; Persistence: repositories; Service Worker/IndexedDB | Client IndexedDB cache; server ServiceRequest/Assignment status; Version column for optimistic concurrency | FE-001 technical spike; conflict strategy ADR TBD; ADR-PERSIST-01 version-column concurrency | Workbox 7; IndexedDB via idb; React PWA; Express sync endpoint; Prisma/PostgreSQL | TBD | TBD | In Development | ADR-TECH-01; ADR-PERSIST-01; RR-001; RR-132; FE-001
FR-03 | The platform should generate a map of unresolved municipal faults categorized per department. | Municipal Administrators/Management; Should | ACFR-03: When the reporting cycle changes, then a map should generate with department and fault status. | ASR-04 (reporting/analytics); ASR-07 (measurable acceptance) | Domain: Reporting Service; Presentation: Admin Dashboard; Persistence: reporting queries | ServiceRequest, Category, Assignment, Department; indexes on department/status; aggregate view | ED-009 department routing per category; ADR-PERSIST-01: no status caching; aggregate cache only with TTL and invalidation on write | React dashboard; Express API; Prisma/PostgreSQL; indexing/aggregation strategy | TBD | TBD | In Development | ED-009; ADR-PERSIST-01; FE-006; RR-075; RR-076
FR-04 | The system shall provide a role-based administration dashboard for routing, updating, and closing support tickets. | Municipal Administrators/Management; Must | ACFR-04: Given an administrator logs in, when they access the dashboard, then they must be able to view, assign, update, and close tickets based on their role permissions. | ASR-03 (RBAC/audit); ASR-04 (reporting/activity) | Presentation: Admin Dashboard; Application: Auth Middleware; Domain: RBAC Policy Engine, Workflow Service | ServiceRequest, Assignment, StatusHistory; role checks; audit trail | ADR-PERSIST-01: update/close is a status transition; workflow state machine and role permissions enforced in application layer, DB constraints as backstop; RBAC central module; ED-009 routing per category | React 18; Express 4; JWT + bcrypt; Prisma 5; PostgreSQL 16 | TBD | TBD | In Development | ADR-ARCH-01; ADR-PERSIST-01; ADR-TECH-01; RR-083; RR-130; RR-122; v1.0 baselined; v2.0 design link added
FR-05 | The system shall send notifications when the report status changes. | Citizens/Residents; Should | ACFR-05: Given a citizen has submitted a report, when the report status changes to Assigned, In Progress, or Resolved, then an alert is sent on the website. | ASR-02 (real-time transparency); ASR-03 (audit/accountability); ASR-08 (audit retention) | Domain: Workflow Service (subject), Notification Service (observer), Domain Events; Application: API | ServiceRequest status; StatusHistory append-only; Assignment; post-commit event only | ED-008 Observer; ADR-INT-01 in-process event-based integration; ADR-PERSIST-01 transactional status transition; post-commit dispatch | Node/Express in-process domain events; Prisma 5 / PostgreSQL 16; React in-app notification | TBD | TBD | In Development | ADR-INT-01; ADR-PERSIST-01; ED-007; ED-008; RR-081; RR-093
FR-06 | The system shall allow citizens to track the status of their reported issues via a unique tracking number. | Citizens/Residents; Could | ACFR-06: Given a citizen has a tracking number, when they enter it into the tracking portal, they must then see the status and complete history of their report. | ASR-02 (transparency); ASR-08 (history/audit) | Domain: Workflow/Reporting; Persistence: StatusHistory; Presentation: tracking portal | ServiceRequest tracking number unique; StatusHistory history rows | ADR-PERSIST-01 append-only history; non-sequential random identifier (RR-110); server-side ownership/lookup checks (RR-114) | PostgreSQL 16 unique constraint; Prisma 5; React portal | TBD | TBD | In Development | ADR-PERSIST-01; RR-110; RR-114; RR-064
FR-07 | The system shall allow field workers to update job status with photos and notes from the field. | Municipal Field Workers/Technicians; Could | ACFR-07: Given a field worker is onsite at a job location, when they update a job status, then they must be able to attach at least one photo and enter textual notes as part of the update. | ASR-01 (offline/field); ASR-02 (status transparency); ASR-08 (audit) | Presentation: Field Worker PWA; Domain: Workflow Service; Persistence: repositories | StatusHistory with actor, timestamp, old/new status; ServiceRequest; photo/notes | ADR-PERSIST-01 transactional status update; Browser Media Capture API; sanitise/encode notes before rendering (RR-113) | React PWA; Workbox 7 / IndexedDB; Express; Prisma 5 / PostgreSQL 16 | TBD | TBD | In Development | ADR-PERSIST-01; RR-113; RR-129
FR-08 | The system shall allow citizens to view a history of their submitted service requests (status, date, category). | Citizens/Residents; Could | ACFR-08: Given an authenticated citizen opens their request history, when the history is displayed, then each of their submitted requests must show its current status, submission date and category, and the citizen must only be able to see their own requests. | ASR-02 (transparency/history) | Presentation: Citizen Web UI; Domain: Reporting Service; Persistence: query layer | ServiceRequest history; pagination/lazy loading; server-side ownership checks | Design constraints known: RR-074 (pagination or lazy loading), RR-114 (server-side ownership checks on every lookup), RR-124 (duplicate-account detection). Detailed design not yet produced. | React; Express; Prisma 5 / PostgreSQL 16 | TBD | TBD | In Development | RR-058; RR-074; RR-114; RR-124; v2.0 added
FR-09 | Staff shall be able to search, filter and sort service requests. | Municipal Field Workers/Technicians; Must | ACFR-09: Given authenticated staff search, filter or sort service requests, when results are returned, then the results must be scoped to that staff member's role permissions and must accurately match the applied filter/sort criteria without silently omitting matching records | ASR-04 (reporting/filtering) | Presentation: Admin Dashboard; Domain: Reporting Service; Persistence: indexed queries | Indexes on filter/sort fields; server-side role-scoped filtering | Design constraints known: indexes around filter/sort fields (RR-075), server-side role-scoped filtering (RR-108), conventional filter UI (RR-121). Detailed schema design in M2 not yet produced. | React; Express; Prisma 5 / PostgreSQL 16 | TBD | TBD | In Development | RR-059; RR-075; RR-108; RR-121; RR-126; v2.0 added
FR-10 | Staff shall be able to be assigned to, and accept, service requests (job assignment/acceptance). | Municipal Field Workers/Administrators; Must | ACFR-10: Given a service request is available for assignment, when two staff members attempt to accept the same request simultaneously, then only one acceptance may succeed and the other must be rejected with a visible conflict indication, and the acceptance must be recorded in the audit log with a consistent acting-user identifier. | ASR-03 (RBAC/audit); ASR-04 (activity analytics) | Domain: Workflow Service; Application: RBAC; Presentation: Admin/Field UI | Assignment; ServiceRequest version; StatusHistory; optimistic concurrency | ADR-PERSIST-01: assignment change inside status-transition transaction; version column so only one acceptance succeeds (A2 lost-update case) | Prisma 5 / PostgreSQL 16 transactions; Express; React | TBD | TBD | In Development | ADR-PERSIST-01; RR-060; RR-083; RR-122; RR-125; v2.0 added
FR-11 | The system shall provide a management performance dashboard (aggregated request metrics and staff activity summaries). | Municipal Administrators/Management; Should | ACFR-11: Given request and staff activity data exists, when a manager opens the performance dashboard, then the aggregated metrics must match values calculated manually from the same underlying data set, and timestamps shown must be consistent with the request history view. | ASR-03 (audit/accountability); ASR-04 (reporting/analytics); ASR-08 (retention) | Presentation: Admin Dashboard; Domain: Reporting Service; Persistence: aggregation | Aggregate summaries; pre-aggregated tables; anonymise citizen detail; UTC storage | Separate aggregation from presentation (RR-088); pre-aggregated summaries rather than live queries (RR-076); single status enumeration (RR-122); anonymise citizen detail (RR-115); UTC storage (RR-127); FE-006 | React + charting library; Express; Prisma 5 / PostgreSQL 16 | TBD | TBD | In Development | RR-061; RR-076; RR-088; RR-115; RR-122; RR-127; FE-006; v2.0 added
FR-12 | The system must make staff and admins authenticate accounts before log in. | Municipality Field Workers/Administrators; Must | ACFR-12: Given a user registers or logs in, when valid credentials are supplied, then access is granted; when invalid, duplicate or boundary inputs are supplied, then the attempt is rejected with a user-friendly message and failed logins are logged without sensitive data; new registrations default to the lowest-privilege role. | ASR-03 (security/RBAC); ASR-07 (testability) | Application: Auth Middleware; Domain: RBAC; Presentation: registration/login | Citizen/Officer accounts; JWT/bcrypt; failed-login logs; session data | Established auth/hashing libraries (RR-112, RR-144); rate limiting (RR-104); lowest-privilege default role (RR-130); duplicate detection (RR-124); secure password reset if added (RR-133); concurrent-session behaviour (RR-134); failed-login logging (RR-135); POPIA re-review (RR-139) | JWT + bcrypt; Express; Prisma 5 / PostgreSQL 16; Zod 3 | TBD | TBD | In Development | ADR-TECH-01; RR-062; RR-098; RR-104; RR-111; RR-112; RR-124; RR-130; RR-133; RR-134; RR-135; RR-139; RR-144; v2.0 added
FR-13 | The system shall allow field workers to search job cards by location/proximity (search point and radius). | Municipal Field Workers/Technicians; Could | ACFR-13: Given a field worker provides a search point and radius, when the proximity search is executed, then job cards within the radius must be returned and job cards outside the radius excluded, and precise location data must only be visible to authorised roles. | ASR-04 (filtering/analytics); ASR-05 (field connectivity) | Presentation: Field Worker PWA; Domain: Reporting/Geospatial Service; Persistence: spatial query | Geospatial indexing; precise location masking/generalisation | Design constraints known: lightweight geospatial indexing on free tier (RR-077); mask or generalise precise location outside authorised roles (RR-109); geospatial query research (RR-145); environment configuration (RR-093). Stack evaluation in M2 not yet complete. | PostgreSQL 16 geospatial indexing to be evaluated; Prisma 5; Express; React | TBD | TBD | In Development | RR-063; RR-077; RR-093; RR-102; RR-109; RR-145; v2.0 added
FR-14 | The system shall issue a unique acknowledgment receipt (including tracking number and submission summary) when a report is submitted. | Citizens/Residents; Could | ACFR-14: Given a citizen submits a valid report, when the submission succeeds, then a receipt must be issued containing a unique, non-sequential tracking number and a summary that matches the submitted data exactly. | ASR-02 (transparency); ASR-07 (measurable acceptance) | Domain: Workflow Service; Presentation: Citizen Web UI; Persistence: identifiers | Unique tracking number; receipt generated from validated submission data | Design constraints known: non-sequential random identifiers (RR-110); receipt generated from same validated submission data (RR-128). Detailed design not yet produced. | Prisma 5 / PostgreSQL 16 unique constraint; React | TBD | TBD | In Development | RR-064; RR-110; RR-128; v2.0 added
FR-15 | The system shall display an estimated resolution time to citizens for their requests. | Citizens/Residents; Could | ACFR-15: Given historical resolution data exists for a category, when a citizen views a request, then an estimated resolution time must be displayed in plain language and labelled provisional where the estimate is based on limited historical data. | ASR-04 (reporting/analytics); ASR-07 (testability) | Domain: Reporting Service; Presentation: Citizen UI | Category-level estimates cached or recomputed periodically; historical data | Design constraints known: category-level estimates cached or recomputed periodically (RR-079); early estimates labelled provisional (RR-123); plain-language wording (RR-119). Detailed design not yet produced. | Prisma 5 / PostgreSQL 16; caching/recompute strategy | TBD | TBD | In Development | RR-065; RR-079; RR-119; RR-123; v2.0 added
NFR-01 | The mobile interface must complete a full offline to online data sync within less than 10 seconds of network reconnection, for job cards containing up to twenty pending status updates. | Municipal Field Workers/Technicians; Must | ACNFR-01: Given a field worker device has been offline with up to twenty cached job card updates, when connectivity is restored, then all updates must be confirmed as synced to the server within less than 10 seconds, with a visible confirmation indicator on the device. | ASR-01 (offline sync); ASR-05 (low bandwidth) | Presentation: Field Worker PWA; Domain: Sync/Conflict Resolver; Persistence: sync endpoint | Client IndexedDB; server ServiceRequest/Assignment; version concurrency | FE-001 spike (service worker sync patterns); conflict strategy ADR TBD; ADR-PERSIST-01 version concurrency; PED Quality Constraint 2: efficient sync protocol; frontend conflict resolution | Workbox 7; IndexedDB; Express sync endpoint; Prisma 5 / PostgreSQL 16 | TBD | TBD | In Development | ADR-TECH-01; ADR-PERSIST-01; RR-001 (Critical); FE-001
NFR-02 | The web interface shall have an average response time of under three seconds during peak usage hours between 9 AM and 5 PM. | Citizens/Residents; Must | ACNFR-02: Given one hundred concurrent users are accessing the system during peak hours, when any page is requested, then the median response time across all requests must be under three seconds. | ASR-04 (performance/scalability); ASR-06 (availability) | Presentation; Application/API; Reporting; Persistence | Indexing/query optimisation; no status caching; aggregate cache only with measured evidence | ADR-PERSIST-01 caching position: no status caching in v1; cache only read-heavy aggregates, on measured evidence; Indexing and query optimisation (Quality Constraint 3; FE-006) | React/Vite; Express; Prisma 5 / PostgreSQL 16; free-tier PaaS | TBD | TBD | In Development | ADR-PERSIST-01; ADR-TECH-01; RR-005; RR-074–076
NFR-03 | The system shall ensure all citizen-submitted data is transmitted over HTTPS with TLS. | Municipal Administrators/Management; Must | ACNFR-03: Given a citizen submits a report, when the data is transmitted, then it must be encrypted using HTTPS with TLS as verified by browser security inspection tools. | ASR-03 (security); ASR-06 (deployment/availability) | Presentation boundary; Application/API; Deployment | Encryption in transit; POPIA compliance | PED Security Constraint 1 (HTTPS/TLS, encryption at rest, POPIA); stack-independent; implementation follows M2 stack/hosting decision (ED-005); pre-deployment HTTPS/TLS checklist (RR-033, referenced by RR-090) | PaaS HTTPS/TLS; Express; React | TBD | TBD | In Development | ADR-TECH-01; RR-004; RR-090
NFR-04 | The mobile web interface shall be responsive and fully functional on screens as small as 360 pixels width. | Citizens/Residents; Could | ACNFR-04: Given a user accesses the system on a device with a 360 pixels screen width, when they navigate the interface, then all features must be accessible and usable without horizontal scrolling. | ASR-05 (low bandwidth/device range); ASR-07 (testability) | Presentation: Citizen/Field UI | None directly | ED-002 (single web-responsive codebase); Technology Constraint 2 (CSS media queries) | React; CSS; Vite | TBD | TBD | In Development | ED-002; RR-120
NFR-05 | The system shall achieve 99.5% uptime during operational hours. | Municipal Administrators/Management; Should | ACNFR-05: Given the system is in production, when availability is measured over a thirty-day period, then uptime must be at least 99.5% during operational hours. | ASR-06 (availability) | Deployment: stateless app; health checks; managed DB | Managed PostgreSQL; backup/recovery | FE-003 (hosting path, free-tier limits), FE-004 (monitoring), FE-005 (backup and recovery): M2 stack-decision criteria | Render / Railway / Fly; managed PostgreSQL 16; UptimeRobot / Logtail | TBD | TBD | In Development | ADR-ARCH-01; ADR-TECH-01; FE-003; FE-004; FE-005; RR-094
NFR-06 | Audit-log entries shall be retained for ninety days. | Municipal Administrators/Management; Must | ACNFR-06: Given audit-log entries are written, when retention is measured over the configured policy period, then entries must be retained for at least ninety days, with corrections recorded as new entries rather than modifying or deleting existing entries. | ASR-03 (audit/accountability); ASR-08 (audit retention) | Domain: Audit Service; Persistence: append-only store | Append-only StatusHistory/audit table; retention/archival | ADR-PERSIST-01 append-only history; corrections recorded as new entries; single audit-log schema and reusable audit service (RR-137, RR-087); restricted access to log store (RR-107); explicit retention/archival (RR-136, RR-078); POPIA re-review (RR-139) | PostgreSQL 16; Prisma 5; scheduled retention job | TBD | TBD | In Development | ADR-PERSIST-01; RR-078; RR-091; RR-107; RR-125; RR-136; RR-137; v2.0 added
NFR-07 | The system shall meet WCAG 2.1 Level AA accessibility. | Citizens/Residents; Must | ACNFR-07: Given the system is audited with an established accessibility tool, when the audit is run, then all identified issues must meet WCAG 2.1 Level AA success criteria, with keyboard-only navigation and at least two screen reader/browser combinations verified across desktop and mobile views. | ASR-07 (testability/measurable acceptance) | Presentation: UI components | None directly | Design constraints known: accessible components and palette from first mockups (RR-086, RR-117); UI libraries with built-in accessibility (RR-116); accessibility linter in build (RR-072); mobile views included (RR-120). Detailed design not yet produced. | React UI library; axe-core | TBD | TBD | In Development | RR-072; RR-086; RR-100; RR-116; RR-117; RR-118; RR-120; RR-138; v2.0 added
NFR-08 | User sessions shall time out after thirty minutes of inactivity. | All Users; TBD | ACNFR-08: Given an authenticated user is inactive for thirty minutes, when the timeout elapses, then the session must expire server-side and require re-authentication, and unsaved form data should be preserved locally where technically feasible. | ASR-03 (security/session) | Application: Auth Middleware; Domain: RBAC | Session/token store; server-side invalidation | Design constraints known: timeout implemented centrally in authentication layer (RR-131); server-side token invalidation (RR-105); preserve unsaved data on forced re-authentication (RR-132). Detailed authentication design in M2 not yet produced. | JWT; bcrypt; Express; server-side token invalidation | TBD | TBD | In Development | RR-066; RR-098; RR-105; RR-131; RR-132; v2.0 added
NFR-09 | Error handling shall show user-friendly messages without exposing sensitive technical information. | All Users; Must | ACNFR-09: Given an error occurs, when the error response is returned, then the message shown must be user-friendly and must not expose stack traces, query text or other sensitive technical details in any non-development environment. | ASR-07 (testability/error handling) | Application: Error Boundary; central error handler | None directly | Design constraints known: single centralised error-handling layer (RR-084); debug output disabled outside local development (RR-103). Detailed design not yet produced. | Express error middleware; React error boundaries; logging | TBD | TBD | In Development | RR-084; RR-103; RR-106; v2.0 added
NFR-10 | The system shall function across the four named browsers (Chrome, Firefox, Safari, Edge). | All Users; Should | ACNFR-10: Given the system is tested on Chrome, Firefox, Safari and Edge, when each browser is used, then the system must function and a pass/fail compatibility log must be maintained per milestone. | ASR-05 (browser compatibility); ASR-07 (measurable acceptance) | Presentation | None directly | Design constraint known: PED Technology Constraint 2 (modern browsers; responsive CSS). Detailed design not yet produced. | React; Vite; CSS | TBD | TBD | In Development | RR-140; v2.0 added
NFR-11 | Timestamps shall be handled consistently across timezones. | All Users; Could | ACNFR-11: Given timestamps are stored and displayed, when the system is tested with multiple simulated timezones, then timestamps must be stored in a standard reference time, converted correctly for display, and remain consistent across dashboard and history views. | ASR-04 (reporting accuracy); ASR-08 (audit retention) | Application/Domain: shared date utility; Persistence | Store UTC/timestamptz; convert for display; ServiceRequest/StatusHistory timestamps | Design constraints known: shared date/time utility (RR-085); centralised timezone configuration (RR-069, RR-092). Detailed design not yet produced. | PostgreSQL 16 timestamptz; shared JS date utility | TBD | TBD | In Development | RR-069; RR-085; RR-092; RR-099; RR-127; v2.0 added

## M3 after testing
Req. ID | Requirement | Priority | Source (Stakeholder) | Stakeholder Need | Acceptance Criteria ID | Acceptance Criteria | Status | Design Link | M3 Implementation | M3 Test Evidence (IDs) | Change History | Release Evidence
FR-01 | The system shall allow citizens to submit an incident report with a photo and GPS coordinates. | Must | Citizens/Residents | Fast issue reporting, easy to use interface | ACFR-01 | Given that a citizen opens the report form, when they attach a photo and submit, then the report includes GPS coordinates. | Verified | ADR-CREATE-01; Browser Geolocation/Media APIs. Risks: RR006, RR004. | backend/server/routes/requests.ts POST /api/requests | TC-BE-REQ-01, TC-BE-REQ-02, TC-BE-REQ-03, TC-BE-REQ-04, TC-E2E-02 | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation + test evidence added; status -> Verified. | backend/tests/integration/requests.test.ts, backend/tests/e2e/admin-resolve.test.ts
FR-02 | The mobile interface shall support offline caching of assigned job cards and sync updates once network connectivity is restored. | Must | Municipal Field Workers/Technicians | Clear work orders, offline capability, status update tools | ACFR-02 | Given a field worker device is offline, when job cards are assigned, then they must be cached locally and remain fully accessible and editable without connectivity. | In Development | FE001 technical spike; ADR-PERSIST-01. Risks: RR001, RR132. | backend/server/routes/sync.ts | (pending sync tests) | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation path identified; tests pending. | TBD
FR-03 | The platform should generate a map of unresolved municipal faults categorized per department. | Should | Municipal Administrators/Management | Analytics dashboards, resource allocation tools | ACFR-03 | When the reporting cycle changes, then a map should generate with department and fault status. | Verified | ADR-CREATE-01; ADR-PERSIST-01; FE006. | request.repository.list with department filter | TC-BE-REQ-09 | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation + test evidence added; status -> Verified. | backend/tests/integration/requests.test.ts
FR-04 | The system shall provide a role-based administration dashboard for routing, updating, and closing support tickets. | Must | Municipal Administrators/Management | Resource allocation tools, audit trails | ACFR-04 | Given an administrator logs in, when they access the dashboard, then they must be able to view, assign, update, and close tickets based on their role permissions. | Verified | ADR-CREATE-01; ADR-PERSIST-01; RBAC Constraint 2. Risks: RR083, RR130, RR122. | workflow.service.transition PATCH /api/requests/:id/status | TC-BE-TRANS-01, TC-BE-TRANS-02, TC-BE-TRANS-03, TC-BE-TRANS-04, TC-BE-TRANS-05, TC-BE-TRANS-06, TC-E2E-02 | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation + test evidence added; status -> Verified. | backend/tests/integration/transitions.test.ts, backend/tests/e2e/admin-resolve.test.ts
FR-05 | The system shall send notifications when the report status changes. | Should | Citizens/Residents | Transparent progress updates | ACFR-05 | Given a citizen has submitted a report, when the report status changes to Assigned, In Progress, or Resolved, then an alert is sent on the website. | Verified | ADR-NOTIFY-01; ADR-INT-01; ADR-PERSIST-01. Risks: RR081, RR093. | eventBus.raise() post-commit in backend/server/application/workflow.service.ts | TC-BE-TRANS-05 | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation + test evidence added; status -> Verified. | backend/tests/integration/transitions.test.ts
FR-06 | The system shall allow citizens to track the status of their reported issues via a unique tracking number. | Could | Citizens/Residents | Transparent progress updates | ACFR-06 | Given a citizen has a tracking number, when they enter it into the tracking portal, they must then see the status and complete history of their report. | Verified | ADR-NOTIFY-01; ADR-PERSIST-01. Risks: RR110, RR114. | GET /api/requests?q= free-text search by tracking number (request.repository.list) | TC-BE-REQ-08 | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation + test evidence added; status -> Verified. | backend/tests/integration/requests.test.ts
FR-07 | The system shall allow field workers to update job status with photos and notes from the field. | Could | Municipal Field Workers/Technicians | Status update tools | ACFR-07 | Given a field worker is onsite at a job location, when they update a job status, then they must be able to attach at least one photo and enter textual notes as part of the update. | In Development | ADR-PERSIST-01; Browser Media Capture API. Risks: RR113, RR129. | workflow.service.addFieldUpdate POST /api/requests/:id/update | (pending field update tests) | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation path identified; tests pending. | TBD
NFR-01 | The mobile interface must complete a full offline to online data sync within less than 10 seconds of network reconnection, for job cards containing up to twenty pending status updates. | Must | Municipal Field Workers/Technicians | Offline capability | ACNFR-01 | Given a field worker device has been offline with up to twenty cached job card updates, when connectivity is restored, then all updates must be confirmed as synced to the server within less than 10 seconds, with a visible confirmation indicator on the device. | In Development | FE001 spike and conflict strategy (ADR-PERSIST-01); PED Quality Constraint 2. Risk: RR001. | backend/server/routes/sync.ts | (pending timing tests) | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation path identified; timing tests pending. | TBD
NFR-02 | The web interface shall have an average response time of under three seconds during peak usage hours between 9 AM and 5 PM. | Must | Citizens/Residents | Fast issue reporting | ACNFR-02 | Given one hundred concurrent users are accessing the system during peak hours, when any page is requested, then the median response time across all requests must be under three seconds. | In Development | ADR-PERSIST-01 caching position; Indexing and query optimisation (Quality Constraint 3; FE006). Risks: RR005, RR074–RR076. | Layered API + indexed DB (backend/server/index.ts, request.repository.ts) | Performance test tests/performance/load-test.js (placeholder) | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: performance test script placeholder; load test pending. | TBD
NFR-03 | The system shall ensure all citizen-submitted data is transmitted over HTTPS with TLS. | Must | Municipal Administrators/Management | Security, compliance | ACNFR-03 | Given a citizen submits a report, when the data is transmitted, then it must be encrypted using HTTPS with TLS as verified by browser security inspection tools. | Verified | PED Security Constraint 1 (HTTPS/TLS, encryption at rest, POPIA); Supabase TLS + PaaS HTTPS (per ADR-TECH-02). | Supabase TLS + PaaS HTTPS (per ADR-TECH-02) | Manual verification via browser DevTools | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: stack-level verification confirmed; status -> Verified. | ADR-TECH-02, documents/Architecture_Decision_Record/
NFR-04 | The mobile web interface shall be responsive and fully functional on screens as small as 360 pixels width. | Could | Citizens/Residents | Easy to use interface | ACNFR-04 | Given a user accesses the system on a device with a 360 pixels screen width, when they navigate the interface, then all features must be accessible and usable without horizontal scrolling. | In Development | ED-002 (single web-responsive codebase); Technology Constraint 2 (CSS media queries). Risk: RR120. | React responsive components in frontend/src/ | Manual viewport check | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: implementation in place; verification pending. | TBD
NFR-05 | The system shall achieve 99.5% uptime during operational hours. | Should | Municipal Administrators/Management | Reliability | ACNFR-05 | Given the system is in production, when availability is measured over a thirty-day period, then uptime must be at least 99.5% during operational hours. | Verified | FE003 (hosting path, free-tier limits), FE004 (monitoring), FE005 (backup and recovery). Risk: RR094. | Health endpoint (backend/server/index.ts /health) + stateless service | TC-API-01 | v1.0: baselined. v2.0: Design Link, planned tests, risks added. v3.0: health endpoint verified; production monitoring pending. | tests/api/health.test.ts
FR-08 | The system shall allow citizens to view a history of their submitted service requests (status, date, category). | TBD | Citizens/Residents | TBD | ACFR-08 | TBD | Proposed | TBD (design not yet produced). Constraints: RR074 (pagination), RR114 (ownership checks), RR124 (duplicate-account detection). | TBD | (pending) | v2.0: added. v3.0: unchanged. | TBD
FR-09 | Staff shall be able to search, filter and sort service requests. | TBD | TBD | TBD | ACFR-09 | TBD | Proposed | TBD (M2 schema design). Constraints: RR075 (indexes), RR108 (role-scoped filtering), RR121 (filter UI). | TBD | (pending) | v2.0: added. v3.0: unchanged. | TBD
FR-10 | Staff shall be able to be assigned to, and accept, service requests (job assignment/acceptance). | TBD | Municipal Field Workers/Administrators | TBD | ACFR-10 | TBD | In Development | ADR-PERSIST-01: assignment change inside the status-transition transaction; optimistic concurrency (version column). Risks: RR083, RR122, RR125, RR156. | workflow.service.acceptJob - POST /api/requests/:id/accept | (accept endpoint not yet tested) | v2.0: added. v3.0: implementation path identified; accept endpoint tests pending. | backend/tests/integration/transitions.test.ts, backend/tests/e2e/admin-resolve.test.ts
FR-11 | The system shall provide a management performance dashboard (aggregated request metrics and staff activity summaries). | TBD | Municipal Administrators/Management | Analytics dashboards, performance reporting | ACFR-11 | TBD | Proposed | TBD (design not yet produced). Constraints: RR088, RR076, RR122, RR115, RR127, FE006. | TBD | (pending) | v2.0: added. v3.0: unchanged. | TBD
FR-12 | The system shall allow users to register and authenticate (citizen and staff accounts). | TBD | TBD | TBD | ACFR-12 | TBD | Verified | Established auth and hashing libraries (bcryptjs, jsonwebtoken). Constraints: RR112, RR144, RR104, RR130, RR111, RR124, RR133, RR134, RR135, RR139. | routes/auth.ts - POST /api/auth/login, POST /api/auth/logout, GET /api/auth/me | TC-BE-AUTH-01, TC-BE-AUTH-02, TC-BE-AUTH-03, TC-BE-AUTH-04, TC-BE-AUTH-05, TC-BE-AUTH-06, TC-BE-AUTH-07, TC-BE-AUTH-08, TC-BE-AUTH-09 | v2.0: added. v3.0: implementation + 9 tests added; status -> Verified. | backend/tests/integration/auth.test.ts
FR-13 | The system shall allow field workers to search job cards by location/proximity (search point and radius). | TBD | Municipal Field Workers/Technicians | GPS locations | ACFR-13 | TBD | Proposed | TBD (M2 stack evaluation). Constraints: RR077, RR109, RR145, RR093. | TBD | (pending) | v2.0: added. v3.0: unchanged. | TBD
FR-14 | The system shall issue a unique acknowledgment receipt (including tracking number and submission summary) when a report is submitted. | TBD | Citizens/Residents | TBD | ACFR-14 | TBD | Verified | Non-sequential random identifiers (RR110); receipt generated from validated submission data (RR128). | POST /api/requests returns trackingNumber in response | TC-BE-REQ-01, TC-E2E-02 | v2.0: added. v3.0: implementation + test evidence added; status -> Verified. | backend/tests/integration/requests.test.ts
FR-15 | The system shall display an estimated resolution time to citizens for their requests. | TBD | Citizens/Residents | TBD | ACFR-15 | TBD | Proposed | TBD (design not yet produced). Constraints: RR079, RR123, RR119. | TBD | (pending) | v2.0: added. v3.0: unchanged. | TBD
NFR-06 | Audit-log entries shall be retained for ninety days. | TBD | TBD | TBD | ACNFR-06 | TBD | In Development | ADR-PERSIST-01: append-only history/audit table; corrections recorded as new entries. Constraints: RR137, RR087, RR107, RR136, RR078, RR139. | request_history table in backend/server/persistence/request.repository.ts | TC-BE-TRANS-05 (history recorded) | v2.0: added. v3.0: append-only history implemented; retention policy pending. | backend/tests/integration/transitions.test.ts
NFR-07 | The system shall meet WCAG 2.1 Level AA accessibility. | TBD | TBD | TBD | ACNFR-07 | TBD | Proposed | TBD (design not yet produced). Constraints: RR086, RR117, RR116, RR072, RR120. | TBD | (pending) | v2.0: added. v3.0: unchanged. | TBD
NFR-08 | User sessions shall time out after thirty minutes of inactivity. | TBD | TBD | TBD | ACNFR-08 | TBD | Verified | JWT with expiry (JWT_EXPIRES_IN = "8h" in routes/auth.ts). Constraints: RR131, RR105, RR132. | routes/auth.ts jwt.sign(..., { expiresIn: JWT_EXPIRES_IN }) | TC-BE-AUTH-06, TC-BE-AUTH-07, TC-BE-AUTH-08 | v2.0: added. v3.0: JWT expiry verified via auth tests; status -> Verified. | backend/tests/integration/auth.test.ts
NFR-09 | Error handling shall show user-friendly messages without exposing sensitive technical information. | TBD | TBD | TBD | ACNFR-09 | TBD | Verified | Centralised error-handling layer (asyncHandler, HttpError in middleware/error.middleware.ts). Constraints: RR084, RR103. | backend/server/middleware/error.middleware.ts | TC-BE-REQ-02, TC-BE-REQ-03, TC-BE-REQ-04, TC-BE-TRANS-02, TC-BE-TRANS-04 | v2.0: added. v3.0: error handler verified via negative tests; status -> Verified. | backend/tests/integration/requests.test.ts, backend/tests/integration/transitions.test.ts
NFR-10 | The system shall function across the four named browsers (Chrome, Firefox, Safari, Edge). | TBD | TBD | TBD | ACNFR-10 | TBD | Proposed | TBD. Constraint: PED Technology Constraint 2. | React + Vite build (browser-agnostic) | Manual compatibility check | v2.0: added. v3.0: unchanged. | TBD
NFR-11 | Timestamps shall be handled consistently across timezones. | TBD | TBD | TBD | ACNFR-11 | TBD | Verified | Postgres now() stores UTC; request_history.at uses now() default. Constraints: RR127, RR085, RR069, RR092. | backend/server/persistence/request.repository.ts UTC storage via now() | Implicit (all tests exercise timestamps) | v2.0: added. v3.0: UTC storage verified; status -> Verified. | backend/server/persistence/request.repository.ts