## Defects
Defect Register — CivicConnect Milestone 3
Owner: Davidzo Malapile, Naledi Moeng, Kamohelo Mabena Version: v1.0 (M3) Last Updated: 2026-10-15
Defect ID | Description | Severity | Status | Fix | Regression Test | State
DEF-001 | Status transitions differ between frontend workflow.ts, routes/requests.ts, and routes/sync.ts — three inconsistent state machine tables | High | Fixed | Created single source of truth in backend/server/domain/workflow.ts (ALLOWED + ROLE_CAN); imported by all routes | TC-BE-WF-01 to TC-BE-WF-20 (20 unit tests) | Closed
DEF-002 | RBAC only allowed field_worker in routes/requests.ts; admins could not assign or reject reports | High | Fixed | Added requireRole("admin", "field_worker") middleware; created role-based transition matrix in workflow.ts | TC-BE-RBAC-01 to TC-BE-RBAC-06 | Closed
DEF-003 | Seed MOCK_STAFF used plaintext passwords instead of bcrypt hashes | Critical | Fixed | Replaced with bcrypt-hashed password verification; seed SQL updated with real hashes | TC-BE-AUTH-01 (valid login succeeds) | Closed
DEF-004 | Fake JWT tokens (dev-token-${id}) instead of real signed tokens | Critical | Fixed | Implemented jsonwebtoken signing with JWT_SECRET; verification in auth.middleware.ts | TC-BE-AUTH-01, TC-BE-AUTH-08 | Closed
DEF-005 | GET /api/auth/me always returned 401 | Medium | Fixed | Implemented JWT verification and user lookup by req.user.id | TC-BE-AUTH-06 | Closed
DEF-006 | No body size limit on express.json() | Medium | Fixed | Set limit: "4mb" for base64 photo payloads | Manual: large photo upload works | Closed
DEF-007 | Unknown keys not stripped from incoming payloads | Low | Fixed | Zod schema validation strips unknown keys via .strict() or .parse() | TC-BE-VAL-01 to TC-BE-VAL-06 | Closed
DEF-008 | No PATCH /api/requests/:id/assign endpoint | High | Fixed | Assignment handled via PATCH /:id/status with assignedTo and assignedName fields | TC-BE-TRANS-01 | Closed
DEF-009 | No filtering support on GET /api/requests | Medium | Fixed | Added q, status, category, department, sort query params to requestRepository.list() | TC-BE-REQ-05 to TC-BE-REQ-09 | Closed
DEF-010 | In-memory store lost data on server restart | Critical | Fixed | Replaced with PostgreSQL persistence via requestRepository, userRepository, teamRepository; deleted store.ts | Manual: server restart preserves reports | Closed
DEF-011 | sync.ts had no transaction; batch could partially apply | High | Fixed | Wrapped sync batch in BEGIN/COMMIT/ROLLBACK | Manual: sync insert + idempotency verified | Closed
DEF-012 | No idempotency on sync — retried batches applied twice | High | Fixed | Added idempotency_keys table; sync checks before processing | Manual: same sync twice returns {"accepted":[]} | Closed
DEF-013 | sync.ts returned 403 on first failure, aborting batch | High | Fixed | Errors are collected and reported per-request; batch continues where safe | TC-BE-SYNC-04 | Closed
DEF-014 | Team validation imported MOCK_STAFF directly instead of DB | High | Fixed | Replaced with userRepository.isActiveFieldWorker() DB check | TC-BE-VAL-05 | Closed
DEF-015 | isAdmin() duplicated in every route file | Medium | Fixed | Centralized as requireRole("admin") middleware | TC-BE-RBAC-01 to TC-BE-RBAC-06 | Closed
DEF-016 | No is_active flag; workers could not be deactivated | Medium | Fixed | Added is_active column to users table; listActiveFieldWorkers() filters by it | Manual: deactivated workers excluded from assignment list | Closed
DEF-017 | authenticatedUser() used O(n) in-memory lookup for token validation | High | Fixed | Replaced with stateless JWT verification (O(1)) | TC-BE-AUTH-01 to TC-BE-AUTH-10 | Closed
DEF-018 | Seed SQL inserted placeholder text (PASTE_WORKER_HASH_HERE) in users.password_hash | High | Fixed | Updated users table with real bcrypt hashes generated via bcryptjs | TC-BE-AUTH-01 | Closed
DEF-019 | requests.ts route handler duplicated the POST / block twice in the file | Low | Fixed | Removed duplicate block; single handler now used | npm run typecheck passes | Closed
DEF-020 | Login rate limiter (10 attempts per 15 min) blocked automated test suites; false 429 responses masked real failures | Low | Fixed | Rate limiter bypassed when DISABLE_RATE_LIMIT=1; threshold raised to 1000 in non-production | TC-BE-AUTH-01 to TC-BE-AUTH-10 | Closed
DEF-021 | Frontend add() wrote only to localStorage; reports never reached the backend API | High | Fixed | Updated src/persistence/requestRepository.ts add() to POST /api/requests; caller in report.tsx awaits the call | Manual E2E: submit via UI → report appears in Supabase | Closed
DEF-022 | Vite import path ./public/styles.css from src/main.tsx resolved incorrectly; frontend failed to load | Medium | Fixed | Changed import to ../public/styles.css | Frontend loads at http://localhost:5173 | Closed
DEF-023 | Root package.json scripts referenced obsolete path src/server/index.ts after backend migration | Medium | Fixed | Updated root scripts to cd backend && npm run dev; added dev:all via concurrently | npm run dev:all starts both services | Closed
DEF-024 | Supabase Direct Connection uses IPv6; failed on team's network | High | Fixed | Switched to Session Pooler connection string (IPv4-compatible) | /health returns {"ok":true,"db":"connected"} | Closed
DEF-025 | Seed SQL inserted placeholder hashes instead of real bcrypt values; login failed with 500 | High | Fixed | Updated users.password_hash with real bcrypt hashes | Login succeeds with valid credentials | Closed
DEF-026 | transitions.test.ts created empty (no describe() block); Vitest reported "No test suite found" | Low | Fixed | Populated with 6 test cases (TC-BE-TRANS-01 to TC-BE-TRANS-06) | All 6 tests pass | Closed
DEF-027 | Password hash verification type cast failed TypeScript strict mode | Low | Fixed | Changed to jwt.JwtPayload & { sub: string; role: Role } intersection type | npm run typecheck passes | Closed
DEF-028 | requestRepository.create() call from requests.ts failed TypeScript structural check | Low | Fixed | Added as ServiceRequest cast with imported type | npm run typecheck passes | Closed

## Defect States
State | Meaning
Open | Identified, not yet fixed
In Progress | Fix under development
Fixed | Code/decision updated, awaiting verification
Verified | Fix confirmed by test/evidence
Closed | Fully resolved; no further action
Won't Fix | Accepted as known limitation (must be justified)

## Severity Scale
Severity | Definition
Critical | Blocks core functionality or exposes security vulnerability; must be fixed before release
High | Significant functional break or data correctness issue; fix required for M3
Medium | Functional gap or quality issue; fix preferred, may be deferred with justification
Low | Cosmetic or minor issue; may be accepted as technical debt

## Summary
Metric | Count
Total defects recorded
Closed (fixed and verified)
Open
Won't Fix
Critical severity
High severity
Medium severity
Low severity
Notes: DEF-001 to DEF-019 identified during M3 backend rewrite; DEF-020 to DEF-028 during M3 test suite construction and frontend integration. All defects closed with regression evidence.